CHAPTER: 1

|  | REFORMS | TIMELINE | CURRENT STATUS |
| --- | --- | --- | --- |
| 1 - E Governance |  |  |  |
| 1 | Creation of Website | Sept 2016 | ULB website has been created http://npprampur.gov.in |
| 2 | Publication of e-newsletter, Digital India Support | Sept 2016 | Monthly e-newsletter are being published on site. http://npprampur.gov.in/documents/budget/npprmpepatrika%20April%202019.pdf |
| 3 | Support Digital India (ducting to be done on PPP mode or by the ULB itself.) | Sept 2016 | ULB supported in the establishment of towers & cables work in the city limit to support Digital India. Various permissionhave been granted to Reliance JIO and Vodafone Esasr to installation of Optical fiber cable in the city. |
| 4 | Coverage with E-MAAS (from the date of hosting the software) - Registration of Birth, Death and Marriage, - Water & Sewerage Charges, - Grievance Redressal, - Property Tax, - Advertisement tax, - Issuance of Licenses, | Mar 2017 | Online Birth & Death registration is going on portal http://edistrict.up.nic.in and http://npprampur.gov.in/Services.html# Marriage registration is going on https://igrsup.gov.in/igrsup/userMarriageRegistration Online water and sewerage charge is being charged on portal http://npprampur.gov.in/Services.html# Grievance Redressal going on web portal - http://jansunwai.up.nic.in/Trackpage.aspx Online Property is collected through NIC portal- http://npprampur.gov.in/Services.html# Offline advertisement tax is being charged Online licenses are issued through portal- http://npprampur.gov.in/Services.html# |

| 4 | - Building Permissions, - Mutations, - Payroll - Pension - e- procurement | Mar 2017 | Offline building permissions are given by RDA after the clearance of NOC from NPP Rampur regarding the land ownership of applicant Online mutation process is going through palika portal http://npprampur.gov.in/Services.html# http://e-nagarsewaup.gov.in/ptaxnpp/ Online transactions through RTGS/NEFT Online transactions through RTGS/NEFT Tenders are invited through E-Tender system and also submitting online. Payments are online. http://npprampur.gov.in/Tenders.html |
| --- | --- | --- | --- |
| 5 | Personnel Staff Management - Online Notification of Recruitment Rules for all municipal cadres - Online Up-to-date Service records/staff Details and seniority lists - Online Bio-metric attendance system | Mar 2018 | Separate Booklet prepared for year 2017-18 |

| 5 |  | 4.Online Employees Grievance redressal system 5. Sou-motu disclosure under RTI Act on website |  | Mar 2018 |  |  | Separate Booklet prepared for year 2017-18 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 6 |  | Project Management - Financial progress - Physical progress 3. Geo-tagging of assets created |  | Mar 2018 |  |  | Separate Booklet prepared for year 2017-18 |
| 2 - Constitution and Professionalization of municipal cadre |  |  |  |  |  |  |  |
| 1 |  | Policy for engagement of interns in ULBs and implementation |  | Sept 2016 |  |  | Policy for engagement of interns in ULBs has been issued as per Govt. Order No.-2034/ukS-5-16-38lk/2016 dated 06-07-2016 |
| 2 |  | Establishment of municipal cadre |  | Mar 2017 |  |  | Municipal Cadre has been established under section 69-B of UP Municipalities Act 1916. |
| 3 |  | Cadre linked training |  | Mar 2017 |  |  | Department wise list of Centralized & non-centralized employees is attached of trained and which are being trained under AMRUT Capacity Building Plan |
| 4 |  | The State will prepare a Policy for Right-sizing the number of municipal functionaries |  | March 2018 |  |  | STATE INITIATIVE |
| 3 - Augmenting Double Entry Accounting |  |  |  |  |  |  |  |
| 1 |  | Complete migration to double entry accounting system and Obtaining an audit certificate to the effect from FY 2012-13 onwards. |  | Sept 2016 |  |  | C.A. have been appointed for the job and completion of the balance sheets from year 2012-13 till 2016-17. http://npprampur.gov.in/documents/budget/Financial%20Statement%202019.pdf |
| 2 |  | Publication of annual financial statement on website |  | Sept 2016 |  |  | Budget from 2012-13 to 2017-18 have been uploaded on ULB website. http://npprampur.gov.in/documents/budget/budget_2018-19.pdf |
| 3 |  | Appointment of internal auditor |  | Mar 2017 |  |  | Internal audit for ULB is being done by ‘Local fund Accounts’ Moradabad. |
| 4 - Urban planning and City Development Plans |  |  |  |  |  |  |  |
| 1 |  | Preparation of SLIP and SAAP |  | Mar 2017 (REPEAT) |  |  | SLIP of Water Supply, Sewerage & Septage Management and Green Space & Park have been prepared and updatedhttp://npprampur.gov.in/documents/SLIP |
| 2 |  | Develop at least one children park every year in the AMRUT cities |  | Mar 2017 (REPEAT) |  |  | Total 9 parks have been developed by palika since 2016. 4 Parks have been selected to develop one in each year under AMRUT. http://npprampur.gov.in/documents/budget/Parks%20MC%20Rampur.pdf |
| 3 |  | Make action plans to progressively increase green cover in cities to 15% in 5 years. |  | March 2016 |  |  | To implement this policy 83 parks have been identified and area under these parks is around 205055S sq. Meter. There is target to increase the green space by 15% till 2019-20. |
| 4 |  | Energy Efficiency Projects |  | June 2017 |  |  | Street light halogen bulbs are replaced by approx 2500 LED bulbs to reduce the power consumption and approx 800 solar switches installed in the city to control the power Wastage. |
| 5 |  | Establish a system for maintaining of parks, playground and recreational areas relying on public private partnerships (PPP) model |  | Sep 2016 |  |  | The parks, playground and recreational areas are maintained by ULB itself. http://npprampur.gov.in/documents/budget/Parks%20MC%20Rampur.pdf |
| 6 |  | Make a State Level policy for implementation the parameters given in the National Mission for sustainable habitat |  | Mar 2017 |  |  | STATE INITIATIVE |
| 7 |  | Establish Urban Development Authorities |  | Mar 2018 |  |  | Separate Booklet prepared for year 2017-18 |
| 5 - Devolution of funds and functions |  |  |  |  |  |  |  |
| 1 |  | Ensure transfer of 14th FC devolution to ULBs |  |  |  |  | The 14th FC fund transferred electronically |
| 2 |  | Appointment of State Finance Commission (SFC) and making decisions |  |  |  |  | Separate Booklet prepared for year 2017-18 |
| 3 |  | Transfer of all function to ULBs |  |  |  |  | Separate Booklet prepared for year 2017-18 |
| 4 |  | Implementation of SFC recommendations within timeline |  | March 2017 |  |  | Separate Booklet prepared for year 2017-18 |
| 6 - Revision of Building Bye-laws |  |  |  |  |  |  |  |
| 1 |  | Revision of Building bye laws periodically |  | Sept 2016 |  |  | https://rdarampur.com/%E0%A4%AD%E0%A4%B5%E0%A4%A8-%E0%A4%A8%E0%A4%BF%E0%A4%B0%E0%A5%8D%E0%A4%AE%E0%A4%BE%E0%A4%A3-%E0%A4%8F%E0%A4%B5%E0%A4%82-%E0%A4%B5%E0%A4%BF%E0%A4%95%E0%A4%BE%E0%A4%B8-%E0%A4%89%E0%A4%AA%E0%A4%B5/ |
| 2 |  | Create single window clearance for all approvals to give building permissions |  | Sept 2016 |  |  | Offline process of map approval/building permissions is followed by RDA. |
| 3 |  | Adoption of Building Bye Laws 2016 |  | March 2017 |  |  | Model Building bye laws 2016 is adopted by Rampur Development Authority. https://rdarampur.com/bye-laws-2016/ |
| 7 - Set-up financial intermediary at state level |  |  |  |  |  |  |  |
| 1 |  | Establish and operationalize financial intermediary- pool finance, access external funds, float municipal bonds. |  | March 2017 |  |  | STATE INITIATIVE |
| 8a - Municipal tax and fees improvement |  |  |  |  |  |  |  |
| 1 |  | At least 90% Coverage & At least 90% Collection |  | Sep 2016 |  | Total properties are 58981, out of which 35790 have been listed for property tax. About 90 % of target has achieved. |  |
| 2 |  | Make policy to periodically revise property tax, levy charges and other fees |  | Sep 2016 |  | STATE INITIATIVE |  |
| 3 |  | Post demand collection book (DCB) of tax details on the website |  | Sep 2016 |  | DCB has been published on ULB website. http://npprampur.gov.in/dcb# |  |
| 4 |  | Achieve full potential advertisement revenue by making a policy for destination specific potential having dynamic pricing module. |  | Sep 2016 |  | Achieved. MC has its advertisement policy to achieve full potential of advertisement revenue. |  |
| 8b - Improvement in levy and collection of user charges |  |  |  |  |  |  |  |
| 1 | Adopt a policy on user charges for individual and institutional assessment in which a differential rate is charged for water use and adequate safeguards are included to take care of interests of the vulnerable. |  | Sep 2016 |  | Different rates are charged for residential and commercial buildings as per Uttar Pardesh Govt gadget notification. |  |  |
| 2 | Make action plan to reduce water losses to less than 20 % and publish on website |  | Sep 2016 |  | ULB is effectively controlling pipeline leakage/water wastage to reduce the loss of water less than 20% |  |  |
| 3 | Separate accounts for user charges |  | Sep 2016 |  | User charges are being deposited online in separate account of ULB. http://e-nagarsewaup.gov.in/ptaxnpp/ |  |  |
| 4 | At least 90 % billing & At least 90%collection |  | Sep 2016 |  | Under Process |  |  |
| 9 – Credit Rating |  |  |  |  |  |  |  |
| 1 | Complete the credit ratings of the ULBs |  | June 2017 |  | The agency (M/s Brickwork Rating Pvt. Ltd.), New Delhi has assigned a rating of IVR BB- (Is) http://npprampur.gov.in/documents/budget/Credit%20Rating.pdf |  |  |
| 10 – Energy and water audit |  |  |  |  |  |  |  |
| 1 | Energy (street lights ) and water audit (including non-revenue water or losses audit) |  | Sept 2016 |  | ESSL is conducting the water audit for ULB. ESSL visited the ULB and collected the required information from ULB. |  |  |
| 2 | Making STPs and WTPs energy efficient |  | Sept 2016 |  | 3 STP have been setup in ULB. http://npprampur.gov.in/documents/budget/Sewerage%20Treatment%20Plants%20Rampur-converted.pdf |  |  |
| 3 | Optimize energy consumption in street lights by using energy efficient lights and increasing reliance on renewable energy |  | Sept 2016 |  | Street light halogen bulbs are replaced by LED bulbs to reduce the power consumption and approx 800 solar switches installed in the city to control the power wastage. |  |  |
| 4 | Waste Water recycling |  | March 2017 |  | Separate Booklet prepared for year 2017-18 |  |  |
| 5 | Faecal Sludge Management |  |  |  | Separate Booklet prepared for year 2017-18 |  |  |
| 11 – Swachh Bharat Mission |  |  |  |  |  |  |  |
| 1 | Elimination of open defecation. |  | March 2018 |  | Separate Booklet prepared for year 2017-18 |  |  |
| 2 | Waste Collection (100%) |  | March 2018 |  |  |  |  |
| 3 | Transportation of Waste (100%). |  | March 2018 |  |  |  |  |
| 4 | Scientific Disposal (100%). |  | March 2018 |  |  |  |  |
| 5 | State Sanitation Policy Notified / City Sanitation Plans prepared |  | March 2018 |  |  |  |  |
| 6 | Percentage of complaints resolution on Swachhta App by ULB |  | March 2018 |  |  |  |  |

CHAPTER: 2

| S N | Reform | Milestones | Current Status | Annexure | Page |
| --- | --- | --- | --- | --- | --- |
| 1 | 1.Urban Planning | a. Develop at least one Children Park every year in AMRUT cities* | Mumtaj park has been developed under Amrut Mission Ambedkar Park and other parks are developed by palika fund. | ANNEX1.1a | 11-14 |
|  |  | b. Preparation of GIS based master plan | State Level |  |  |
| 2 | 2.Double Entry Accounting System | a. Publication of Annual budget on website. b. Publication of audited balance sheet on website. | Annual Budget from year 2013 to 2018 have been published on MC site. Screenshots have been attached http://npprampur.gov.in/documents/budget/budget_2018-19.pdf Balance sheets are on MC website.Screenshots have been attached. http://npprampur.gov.in/documents/budget/Balance%20Sheet%202016-2017.pdf | ANNEX2.2 .a.1 ANNEX2.2.b | 15-16 17-22 |

Annexure1.1

Annexure2.2.a

Annexure2.2.b